## Sheet1
|  | 2022 |  |  | 2023
| Effort by Nick A | October | November | December | January | February | March | April | May
Analyze structure of current DB | 100% | 2022 November: Nov 15 - Dec 15
Design layout of new DB | 100% | bar: 2022 November to 2022 December
Analyze output features included in current sol'n | 100% | bar: 2022 November to 2022 December
Discuss desired features with userbase | 100% | bar: 2022 November to 2022 December
List primary output features of project | 100% | 2022 December: 1 - 15
Research C++ GUI development, exe creation | 100% | 2023 January: Jan 15 - Feb 15
Research proper ways to communicate C++->SQL | 100% | bar: 2023 January to 2023 February
Create the database | 100% | 2023 February: 16 - 17
Create the basic GUI homepage | 100% | 2023 February: 20 - 24
Implement rent collections | 100% | 2023 February: Feb 27 - March 17
Implement water, gas tracking | 100% | 2023 March: 17 - 31
Polish the application visually | 100% | 2023 April: 3 - 21ish
Deliver | 100% | 2023 May: 3